## 工作表1
The Following works will be ready for inspection on
Form No. | Request No. (RIW-) | Date of Submission |  |  | Location | Description of Works | Works proposed after inspection | Contact Person | Contact Number | Project Specific Code | Main works Category | Sub-works Category | ITAP Code
|  |  | 2024-04-06 | 9:00 | Zone 2 Block 7A G/F MIC (S7-G/F- 001 to S7-G/F-044 ) | Coupler Condition Before Rebar Installation at G/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-06-18 | 9:00 | Zone 2 Block 7A 1/F MIC (S7-G/F- 001 to S7-G/F-044 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-08 | 9:00 | Zone 2 Block 7A R/F MIC (S7-2/F- 001 to S7-2/F-044 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-08 | 9:00 | Zone 2 Block 7A R/F MIC (S7-2/F- 001 to S7-2/F-044 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-10 | 9:00 | Zone 2 Block 7B G/F MIC (S7-G/F- 045 to S7-G/F-116 ) | Coupler Condition Before Rebar Installation at G/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-14 | 9:00 | Zone 2 Block 7B 1/F MIC (S7-G/F- 045 to S7-G/F-116 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-14 | 9:00 | Zone 2 Block 7B 1/F MIC (S7-G/F- 045 to S7-G/F-116 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-14 | 9:00 | Zone 2 Block 7B 1/F MIC (S7-G/F- 045 to S7-G/F-116 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-20 | 9:00 | Zone 2 Block 7B 2/F MIC (S7-1/F- 045 to S7-1/F-116 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-20 | 9:00 | Zone 2 Block 7B 2/F MIC (S7-1/F- 045 to S7-1/F-116 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-20 | 9:00 | Zone 2 Block 7B 2/F MIC (S7-1/F- 045 to S7-1/F-116 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-24 | 9:00 | Zone 2 Block 7B R/F MIC (S7-2/F- 045 to S7-2/F-116 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-24 | 9:00 | Zone 2 Block 7B R/F MIC (S7-2/F- 045 to S7-2/F-116 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-24 | 9:00 | Zone 2 Block 7B R/F MIC (S7-2/F- 045 to S7-2/F-116 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-26 | 9:00 | Zone 2 Block 7F G/F MIC (S7-G/F- 117 to S7-G/F-128 ) | Coupler Condition Before Rebar Installation at G/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-26 | 9:00 | Zone 2 Block 7F 1/F MIC (S7-G/F- 117 to S7-G/F-128 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-26 | 9:00 | Zone 2 Block 7F 1/F MIC (S7-G/F- 117 to S7-G/F-128 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-26 | 9:00 | Zone 2 Block 7F 1/F MIC (S7-G/F- 117 to S7-G/F-128 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-05 | 9:00 | Zone 2 Block 7F 2/F MIC (S7-1/F- 117 to S7-1/F-128 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-05 | 9:00 | Zone 2 Block 7F 2/F MIC (S7-1/F- 117 to S7-1/F-128 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-05 | 9:00 | Zone 2 Block 7F 2/F MIC (S7-1/F- 117 to S7-1/F-128 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-07 | 9:00 | Zone 2 Block 7F R/F MIC (S7-2/F- 117 to S7-2/F-128 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-07 | 9:00 | Zone 2 Block 7F R/F MIC (S7-2/F- 117 to S7-2/F-128 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-07 | 9:00 | Zone 2 Block 7F R/F MIC (S7-2/F- 117 to S7-2/F-128 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-27 | 9:00 | Zone 2 Block 7E G/F MIC (S7-G/F- 129 to S7-G/F-140 ) | Coupler Condition Before Rebar Installation at G/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-29 | 9:00 | Zone 2 Block 7E 1/F MIC (S7-G/F- 129 to S7-G/F-140 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-29 | 9:00 | Zone 2 Block 7E 1/F MIC (S7-G/F- 129 to S7-G/F-140 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-29 | 9:00 | Zone 2 Block 7E 1/F MIC (S7-G/F- 129 to S7-G/F-140 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-30 | 9:00 | Zone 2 Block 7E 2/F MIC (S7-1/F- 129 to S7-1/F-140 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-30 | 9:00 | Zone 2 Block 7E 2/F MIC (S7-1/F- 129 to S7-1/F-140 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-30 | 9:00 | Zone 2 Block 7E 2/F MIC (S7-1/F- 129 to S7-1/F-140 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-02 | 9:00 | Zone 2 Block 7E R/F MIC (S7-2/F- 129 to S7-2/F-140 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-02 | 9:00 | Zone 2 Block 7E R/F MIC (S7-2/F- 129 to S7-2/F-140 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-02 | 9:00 | Zone 2 Block 7E R/F MIC (S7-2/F- 129 to S7-2/F-140 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-27 | 9:00 | Zone 2 Block 7D G/F MIC (S7-G/F- 141 to S7-G/F-152 ) | Coupler Condition Before Rebar Installation at G/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-30 | 9:00 | Zone 2 Block 7D 1/F MIC (S7-G/F- 141 to S7-G/F-152 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-30 | 9:00 | Zone 2 Block 7D 1/F MIC (S7-G/F- 141 to S7-G/F-152 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-30 | 9:00 | Zone 2 Block 7D 1/F MIC (S7-G/F- 141 to S7-G/F-152 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-31 | 9:00 | Zone 2 Block 7D 2/F MIC (S7-1/F- 141 to S7-1/F-152 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-31 | 9:00 | Zone 2 Block 7D 2/F MIC (S7-1/F- 141 to S7-1/F-152 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-31 | 9:00 | Zone 2 Block 7D 2/F MIC (S7-1/F- 141 to S7-1/F-152 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-02 | 9:00 | Zone 2 Block 7D R/F MIC (S7-2/F- 141 to S7-2/F-152 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-02 | 9:00 | Zone 2 Block 7D R/F MIC (S7-2/F- 141 to S7-2/F-152 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-02 | 9:00 | Zone 2 Block 7D R/F MIC (S7-2/F- 141 to S7-2/F-152 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-26 | 9:00 | Zone 2 Block 7C G/F MIC (S7-G/F- 153 to S7-G/F-164 ) | Coupler Condition Before Rebar Installation at G/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-26 | 9:00 | Zone 2 Block 7C 1/F MIC (S7-G/F- 153 to S7-G/F-164 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-26 | 9:00 | Zone 2 Block 7C 1/F MIC (S7-G/F- 153 to S7-G/F-164 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-26 | 9:00 | Zone 2 Block 7C 1/F MIC (S7-G/F- 153 to S7-G/F-164 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-28 | 9:00 | Zone 2 Block 7C 2/F MIC (S7-1/F- 153 to S7-1/F-164 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-28 | 9:00 | Zone 2 Block 7C 2/F MIC (S7-1/F- 153 to S7-1/F-164 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-28 | 9:00 | Zone 2 Block 7C 2/F MIC (S7-1/F- 153 to S7-1/F-164 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-29 | 9:00 | Zone 2 Block 7C R/F MIC (S7-2/F- 153 to S7-2/F-164 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-29 | 9:00 | Zone 2 Block 7C R/F MIC (S7-2/F- 153 to S7-2/F-164 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-29 | 9:00 | Zone 2 Block 7C R/F MIC (S7-2/F- 153 to S7-2/F-164 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-10 | 9:00 | Zone 2 Block 8A 1/F MIC (S8-G/F- 001 to S8-G/F-036 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-10 | 9:00 | Zone 2 Block 8A 1/F MIC (S8-G/F- 001 to S8-G/F-036 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-10 | 9:00 | Zone 2 Block 8A 1/F MIC (S8-G/F- 001 to S8-G/F-036 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-21 | 9:00 | Zone 2 Block 8A 2/F MIC (S8-1/F- 001 to S8-1/F-036 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-21 | 9:00 | Zone 2 Block 8A 2/F MIC (S8-1/F- 001 to S8-1/F-036 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-21 | 9:00 | Zone 2 Block 8A 2/F MIC (S8-1/F- 001 to S8-1/F-036 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-21 | 9:00 | Zone 2 Block 8A R/F MIC (S8-2/F- 001 to S8-2/F-036 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-21 | 9:00 | Zone 2 Block 8A R/F MIC (S8-2/F- 001 to S8-2/F-036 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-21 | 9:00 | Zone 2 Block 8A R/F MIC (S8-2/F- 001 to S8-2/F-036 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-11 | 9:00 | Zone 2 Block 8C 1/F MIC (S8-G/F- 037 to S8-G/F-048 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-11 | 9:00 | Zone 2 Block 8C 1/F MIC (S8-G/F- 037 to S8-G/F-048 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-11 | 9:00 | Zone 2 Block 8C 1/F MIC (S8-G/F- 037 to S8-G/F-048 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-13 | 9:00 | Zone 2 Block 8C 2/F MIC (S8-1/F- 037 to S8-1/F-048 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-13 | 9:00 | Zone 2 Block 8C 2/F MIC (S8-1/F- 037 to S8-1/F-048 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-13 | 9:00 | Zone 2 Block 8C 2/F MIC (S8-1/F- 037 to S8-1/F-048 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-16 | 9:00 | Zone 2 Block 8C R/F MIC (S8-2/F- 037 to S8-2/F-048 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-16 | 9:00 | Zone 2 Block 8C R/F MIC (S8-2/F- 037 to S8-2/F-048 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-16 | 9:00 | Zone 2 Block 8C R/F MIC (S8-2/F- 037 to S8-2/F-048 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-12 | 9:00 | Zone 2 Block 8D 1/F MIC (S8-G/F- 049 to S8-G/F-052 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-12 | 9:00 | Zone 2 Block 8D 1/F MIC (S8-G/F- 049 to S8-G/F-052 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-12 | 9:00 | Zone 2 Block 8D 1/F MIC (S8-G/F- 049 to S8-G/F-052 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-20 | 9:00 | Zone 2 Block 8D 2/F MIC (S8-1/F- 049 to S8-1/F-052 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-20 | 9:00 | Zone 2 Block 8D 2/F MIC (S8-1/F- 049 to S8-1/F-052 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-20 | 9:00 | Zone 2 Block 8D 2/F MIC (S8-1/F- 049 to S8-1/F-052 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-25 | 9:00 | Zone 2 Block 8D R/F MIC (S8-2/F- 049 to S8-2/F-052 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-25 | 9:00 | Zone 2 Block 8D R/F MIC (S8-2/F- 049 to S8-2/F-052 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-25 | 9:00 | Zone 2 Block 8D R/F MIC (S8-2/F- 049 to S8-2/F-052 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-24 | 9:00 | Zone 2 Block 8B 1/F MIC (S8-G/F- 077 to S8-G/F-088 ) | Coupler Condition Before Rebar Installation at 1/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-24 | 9:00 | Zone 2 Block 8B 1/F MIC (S8-G/F- 077 to S8-G/F-088 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-24 | 9:00 | Zone 2 Block 8B 1/F MIC (S8-G/F- 077 to S8-G/F-088 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-24 | 9:00 | Zone 2 Block 8B 2/F MIC (S8-1/F- 077 to S8-1/F-088 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-24 | 9:00 | Zone 2 Block 8B 2/F MIC (S8-1/F- 077 to S8-1/F-088 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-24 | 9:00 | Zone 2 Block 8B 2/F MIC (S8-1/F- 077 to S8-1/F-088 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-09-26 | 9:00 | Zone 2 Block 8B R/F MIC (S8-2/F- 077 to S8-2/F-088 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-09-26 | 9:00 | Zone 2 Block 8B R/F MIC (S8-2/F- 077 to S8-2/F-088 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-09-26 | 9:00 | Zone 2 Block 8B R/F MIC (S8-2/F- 077 to S8-2/F-088 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-27 | 9:00 | Zone 2 Block 9A 2/F MIC (S9-1/F- 001 to S9-1/F-036 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-27 | 9:00 | Zone 2 Block 9A 2/F MIC (S9-1/F- 001 to S9-1/F-036 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-27 | 9:00 | Zone 2 Block 9A 2/F MIC (S9-1/F- 001 to S9-1/F-036 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-31 | 9:00 | Zone 2 Block 9A R/F MIC (S9-2/F- 001 to S9-2/F-036 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-31 | 9:00 | Zone 2 Block 9A R/F MIC (S9-2/F- 001 to S9-2/F-036 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-25 | 9:00 | Zone 2 Block 9C 1/F MIC (S9-G/F- 037 to S9-G/F-060 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-25 | 9:00 | Zone 2 Block 9C 1/F MIC (S9-G/F- 037 to S9-G/F-060 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-05 | 9:00 | Zone 2 Block 9C 2/F MIC (S9-1/F- 037 to S9-1/F-060 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-08 | 9:00 | Zone 2 Block 9C R/F MIC (S9-2/F- 037 to S9-2/F-060 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-08 | 9:00 | Zone 2 Block 9C R/F MIC (S9-2/F- 037 to S9-2/F-060 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-08 | 9:00 | Zone 2 Block 9C R/F MIC (S9-2/F- 037 to S9-2/F-060 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-30 | 9:00 | Zone 2 Block 9D 2/F MIC (S9-1/F- 061 to S9-1/F-096 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-30 | 9:00 | Zone 2 Block 9D 2/F MIC (S9-1/F- 061 to S9-1/F-096 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-30 | 9:00 | Zone 2 Block 9D 2/F MIC (S9-1/F- 061 to S9-1/F-096 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-02 | 9:00 | Zone 2 Block 9D R/F MIC (S9-2/F- 061 to S9-2/F-096 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-26 | 9:00 | Zone 2 Block 9B 2/F MIC (S9-1/F- 097 to S9-1/F-120 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-26 | 9:00 | Zone 2 Block 9B 2/F MIC (S9-1/F- 097 to S9-1/F-120 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-26 | 9:00 | Zone 2 Block 9B 2/F MIC (S9-1/F- 097 to S9-1/F-120 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-03 | 9:00 | Zone 2 Block 9B R/F MIC (S9-2/F- 097 to S9-2/F-120 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-08-03 | 9:00 | Zone 2 Block 9B R/F MIC (S9-2/F- 097 to S9-2/F-120 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-03 | 9:00 | Zone 2 Block 9B R/F MIC (S9-2/F- 097 to S9-2/F-120 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-06-21 | 9:00 | Zone 2 Block 10A 1/F MIC (S10-G/F- 021 to S10-G/F-040 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-06-28 | 9:00 | Zone 2 Block 10A 2/F MIC (S10-1/F- 001 to S10-1/F-003 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-17 | 9:00 | Zone 2 Block 10A R/F MIC (S10-2/F- 001 to S9-2/F-017 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-17 | 9:00 | Zone 2 Block 10A R/F MIC (S10-2/F- 021 to S9-2/F-040 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-17 | 9:00 | Zone 2 Block 10A R/F MIC (S9-2/F- 018 to S9-2/F-040 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-17 | 9:00 | Zone 2 Block 10A R/F MIC (S9-2/F- 001 to S9-2/F-040 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-06-29 | 9:00 | Zone 2 Block 10B 1/F MIC (S10-G/F- 057 to S10-G/F-060 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-13 | 9:00 | Zone 2 Block 10B 2/F MIC (S10-1/F- 057 to S10-1/F-072 ) | Coupler Condition Before Rebar Installation at 2/F | Rebar Installation | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-13 | 9:00 | Zone 2 Block 10B 2/F MIC (S10-1/F- 057 to S10-1/F-072 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-13 | 9:00 | Zone 2 Block 10B 2/F MIC (S10-1/F- 057 to S10-1/F-072 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-17 | 9:00 | Zone 2 Block 10B R/F MIC (S10-2/F- 041 to S10-2/F-072 ) | Coupler Condition Checking | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-8 - Coupler Condition Checking (Before Re...
|  |  | 2024-07-17 | 9:00 | Zone 2 Block 10B R/F MIC (S10-2/F- 057 to S10-2/F-072 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-17 | 9:00 | Zone 2 Block 10B R/F MIC (S10-2/F- 041 to S10-2/F-072 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-08-05 | 9:00 | Zone 2 Block 10C 1/F MIC (S10-G/F- 073 to S10-G/F-094 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-08-05 | 9:00 | Zone 2 Block 10C 1/F MIC (S10-G/F- 073 to S10-G/F-094 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection
|  |  | 2024-07-11 | 9:00 | Zone 2 Block 10C R/F MIC (S10-2/F- 073 to S10-2/F-116 ) | Inspection of installed coupler system connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-4 - Rebar/Coupler System Installation Che...
|  |  | 2024-07-11 | 9:00 | Zone 2 Block 10C R/F MIC (S10-2/F- 073 to S10-2/F-116 ) | Inspection of Torque Test for Bolt Connection | - | Chow Ka Fai | 69339321 | SSM518 | structure | Others | S-MiC-10 - Torque Test for Bolt Connection